## Action Log
St Bride's School & Nursery Parent Council - Rolling Action and Decision Log
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement | Supporting Documentation
PC01 | 06.03.2024 | LT provided update via monthly HT report | LT |  |  |  |  | 06.11.2024 Further to the HT monthly report, LT shared a presentation on 'Attachement-Informed, Trauma Sensitive' with the Parent Council
PC51 | 07.05.2025 | PC Banner | NE/PF | Ongoing |  |  | It was discussed how we can be more visible to the parents . NE/PF said that they had already looked into a banner that can be displayed outside school to have hold a copy of newsletter/important information. CL said a physical copy of a newsletter would be good. LT said these could possibly be displayed outside school as well as school monthly newsletter. LR also thought that creating posts on our social media with a picture and a little blurb of information about ourselves could possibly make us more visible and known to other parents. PF has asked all PC members if they could provide this information for posting. 03.09.2025 NE will chase up the design of the banner and over the next couple of weeks will begin introducing members on our Social Media pages. 01.10.2025 NE is aware this still needs to be sketched and will try her best to complete sketch for next PC meeting. 13.11.2025 NE apologised as this has still not been completed and will try her best to have an update for the next meeting. 04.02.2026 NE to progress at the earliest oppotunity 06.05.2026 NE has been unable to make any progress on this item due to other commitments but will seek to do this as soon as possible. 03.06.2026 No progress has yet been made on this agenda item and will be carried on to the next term.
PC55 | 01.10.2025 | Funding | PC/SMcG | Ongoing |  |  | PC reviewed the funding options which we have looked into and why as a PC we didn't take them any further. SM will look into other funding options which could be open to the PC and the school and will report back at next PC meeting. 13.11.2025 SM apologised that he only did a small amount of research and will continue to look into all available funding. He did report back on funding from Co-op/Scotmid and Asda. SM will compile this findings. PC may ask school and children for a wishlist so that we can focus our funding on certain projects. 04.02.2026 PC discussed a potential funding opportunity via SCOTMID, SMcG to progress for submission deadline 04.03.2026 SMcG presented his proposed application on behalf of the PC. Discussion took place around specific outdoor and/or equipment requirements. SMcG to contact Kirkihill Tennis Club around a previous competition win where they provided a tennis wall to gauge cost. 06.05.2026 SMcG updated PC regarding the Scotmid funding application. He advised that, due to a high volume of community grant applications in April, the funding round was closed earlier than anticipated. However, the application will be considered at the next meeting in June, and, if successful, the funds will be transferred within one week. 03.06.2026 SMcG notified the PC that he had communication with Scotmid grant stating that if we were successful in our bid we would find out by Monday or Tuesday and the money would be in our account by the next day.
PC57 | 13.11.2025 | MSP/Councillor invite to future PC meeting | NE/PF | 02.09.2026 |  |  | PC addressed the idea of contacting local politicians and councillors, inviting them to our PC meeting and using their knowledge to aid us with the running and fundraising for the school. We will maybe invite to February meeting. 08.01.2026 PC will send the dates and times of the meetings to the relevant councillors along with the agenda as an invitation. 04.02.2026 NE to progress this for the later part of this year after 2026/27 school lets have been agreed 04.03.2026 As above this item will be progressed taking into account the forthcoming local election perimeters. 06.05.2026 Due to the Scottish Elections and almost at the end of the school year, we will strive to this at the start of the next term. 03.06.2026 It was agreed the NE will contact the MSP and invite them to attend the AGM at the beginning of the new term.
PC63 | 04.02.2026 | End of Term Ice Cream Van | PC/NE | 03.06.2026 |  |  | PC to book the annual ice cream van for all School and Nursery pupils and staff. NE to organise booking 04.03.2026 NE confirmed the ice cream van is booked as requested and will be onsite at 0930 03.06.2026 The expected number of staff and pupils from school and nursery has been given to the ice cream van vendor who has subsequently confirmed their attendance. Invoices will be given to JH.
PC65 | 04.02.2026 | PC Constitution | PC/CB | Ongoing |  |  | PC to undertake and update and re-write of the current PC Constitution in order to mordanise and support future planned application to necome a registered charity. CB will undertake this piece of work 04.03.2026 CB still progressing this indepth piece of work and will provide an update at the earliest opportunity 06.05.2026 CB has complted the first draft of the constitution, which the PC will review and provide comments on, He has also prepared a list outling the advantages and disadvantages if obtaining charitable status. 03.06.2026 PC will meet off table to discuss this item after the AGM.
PC67 | 04.02.2026 | School Sports Day | PC | 03.06.2026 |  |  | PC proposed a fundraising opportunity offering refreshements to parents/carers at the forthcoming planned school sports day, this will be weather dependant and assessed nearer the time 03.06.2026 Following discussion, the Parent Council agreed that, due to the unpredicatable nature of the weather, it would be difficult to organise a Parent Council event at this time.
PC68 | 04.02.2026 | Parent Lottery Introduction | PC | 04.03.2026 |  |  | PC are keen to launch to previously discussed 'Parents Lottery' tIto the school and Nursery in conjunction with ParentKind (PTA Fundraising Association), further details will be shared in due course 04.03.2026 The PC will seek to progress this item after the Easter break 06.05.2026 PF will update the PC at the next meeting regarding any developments. 03.06.2026 It was agreeed that the co-chairs would introduce the Parent Lottery to the parents of the new P1 intake and raise awareness of the initiative across the school at the beginning of the new term,
PC69 | 04.02.2026 | PC Fundraising Activities | PC | 03.06.2026 |  |  | PC shared some forthcoming findraising opportunities: - World Cup Colouring Competition -Friday (school close) Beat the Goalie -Friday Ice Lolly/Pole stand More details will follow 06.05.2026 Further discussion took place regarding ideas for an after school World Cup fundraiser, including possibly having high school pupils act as goalkeepers and running a raffle for World Cup themed prizes, with tickets being sold during school time. HT offered to display the prizes on the stairs noting that this is their usual approach for raffles and helps to generate interest. 03.06.2026 The PC will run a Penny Wars fundraising event in October, involving all classes. Further details will be provided in due course. Following a review of available dates and manpower, the PC agreed to amend the planned World Cup fundraising event, as it was not possible to secure a suitable date for an end of day event. As an alternative, and in-school raffle will be held. The PC will provide a range of football and Scotland themed prizes, with a £75 JD Sports voucher as the star prize.
PC70 | 04.02.2026 | School Car Parking | ALL | Ongoing |  |  | PC raised concerns over the ongoing school parking at school/nursery pick up time. The combination of the recent Council ruling over no pavement parking, local business and medical centre, Police station re-opening, bollards on school lollipop man crossing along with some irresponsible parking are contributing to school exit safety concerns. PC suggested the introduction of a drop-off/pick-up zone within the school/nursery car park. The HT advised that the car park is designated for school staff and visitors only, with no allocated parking for parents. The HT noted that there are over 200 families across the school and nursery, and that operating a drop-off/pick-up zone at the start and end of the school day would not be practical. The HT further advised that she has received parental complaints regarding parking in the vicinity of the school, which have been escalated to SLC Headquarters. She confirmed that the car park operates in line with arrangements at other schools within the Learning Community. The HT also advised that she has requested a traffic survey be undertaken by SLC to assess parking concerns, and that the results will be shared once available. 04.03.2026 Further discussion took place around this item and theassociated challenges. challenges. HT advised tthe council will carry out a Traffic management audit commencing next term along with school inspection. HT advised of several conversations with parents seeking to use the school car park along with challenges to our Janitor regarding this. HT is seeking to send out a communication to parents/carers which the PC support 06.05.2026 HT confirmed that the audit had been carried out and HT is awaiting the report. She will advise the PC of the outcome once she has received the audit report, hopefully at the next PC meeting. 03.06.2026 HT has received the report and commented on the findings to the PC. It has been noted that any work that needs addressed has to be completed by the Roads Department. HT reinforced that it is up to the parents and carers to park legally and responsibly. Another further complaints to do be made to council and police.
PC72 | ` | Mobile Phone use in School | ALL | Ongoing |  |  | The Headteacher (HT) advised that she had consulted with school staff regarding the development of a Mobile Device Policy. She also confirmed that pupils will be consulted as part of this process. The Parent Council (PC) confirmed their support for this approach. The HT will draft a communication outlining the consultation and will report back to the PC. The Mobile Device Policy is scheduled to be introduced by August 2026. 06.05.2026 HT has created a Mobile Device Policy. She is still required to consult staff and then will share with PC at the next meeting. 03.06.2026 HT issued the PC with a copy of the new mobile phone policy. It has been noted that due to the forthcoming Scottish Government guidance and legislation, this policy will require review and revision once the new requirements are in place.
PC74 | 06.05.2026 | School Photographer | PC | ongoing |  |  | PF had commented that there as a change in the quality of photographs from the current photographer. PC discussed the possiblity of changing photographer. PC will research any other photographers available and maybe obtain a portfolio. 03.06.2026 PC have been unable to gather portfolio for new prospective school photographer so therefore this will carry on to the new term
PC75 | 06.05.2026 | Church Representative | PC |  |  |  | With Father Gerry's return, it would be benefical for the Parent Council to in roduce ourselves. We should also take this opportunity to discuss the role of the church representative. 03.06.2026 LR and PF introduced themselves to Father Gerry. He expressed an interest in the PC and would come along to future meetings himself.
PC76 | 03.06.2026 | P1 Parent Gifts | PF | 13.08.2026 |  |  | PF has confirmed she is able to prepare the gifts for the new P1 parents and will be able to distribut them on the first day of the new term.
PC 77 | 03.06.2026 | Thank you to John Hyland | PC |  |  |  | The PC would like to extend its sincere thanks to John, our Treasurer, who has made the difficult decision to step down from his role. We would like to express our gratitude for the 6 years of dedicated service he has given to the committee. His commitment, careful management of budgets, and the many other responsibilites he has undertaken have been greatly valued and appreciated, We thank John for all his hard work and wish him every success for the future.

## Decision Log
Decision Rolling LOG: St Bride's School & Nursery Parent Council
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement | Supporting Documentation
PC12 | 06.03.2024 | PC Minutes - LT advised of recent parental feedback regarding visibility of PC monthly meeting discussions. PC proposed moving from a minutes template to that of a rolling action and decision log which can be updated within the meeting and shared within the PC update of the HTs monthly newsletter and be shared on school website, the group agreed to progress | PF | 01.05.2024 |  | Decision | PF to provided template for update 01.05.2024 Template shared, logos to be used on all future documentation
PC15 | 06.03.2024 | Maths Game Competition - Mr Nugent has requested prize funding support for the forthcoming Maths competition on 14.03.2024. The PC agreed to a £100 donation. |  | 01.05.2024 |  | Decision | JH to provide £100 to LT
PC 39 | 08.01.2025 | Lets for PC meetings | PF/NE/LT | 04.06.2025 | 07.05.2025 |  | PF and NE will meet with LT to arrange the dates for the lets for the PC meetings for the forthcoming school year. 05.03.2025 LT suggested that mid-end May this meeting should take place to allow her to submit our requests within the timescales. PF and NE to confirm a date to meet 07.05.2025 PF and NE have provisionally created a list of dates for meeting and events.

## Closed Log
ROLLING Closed LOG: St Bride's School & Nursery Parent Council
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement | Supporting Documentation
PC04 | 06.03.2024 | PC confirmed Easter Bonus Ball initiative which will run during Parent Reporting Evening on 2103.2024. LT advised Nursery school will also support the sale of this. PC requested this is publicised via school X (Twittter) and Parent Portal | PF/LT | 01.05.2024 |  |  | PF to provide Bonus Ball sheets to LT for Nursery sales and PC will pick up from office on Parent Reporting Evening for school parents/carers participation 01.05.2024 Easter Bonus Ball generated £231 with the lucky winner sharing half of the winnings (notified)
PC09 | 06.03.2024 | End of term ice cream van - PC suggested they purchase ice lollies rather than the use of the ice cream van to keep cost down however, it was agreed that the van was a nice end of term treat. PC to contact some ice van sellers for costing/availability including the one used at Halfway Fireworks. Total school number including staff 380. | LR | 01.05.2024 |  |  | LR to obtain numbers and contact for costs 01.05.2024 Ice cream van booked for Friday 21 June 0930-1130
PC02 | 06.03.2024 | JH provided update regarding PC finance position and completion of Bank signatory forms now updated | JH | 05.06.2024 |  |  | JH advised current funds in PC bank account is £2600. Discussion took place around maintaining this to allow continued support to school requests and PC events.Bank signatory forms updated and previous signatories to be removed which JH/NE will undertake 01.05.24 JH advised this action will be completed by the end of this week 05.06.2024 The action of signatory forms is now complete.
PC06 | 06.03.2024 | PC Banner request was discussed which would be visible in events with LT advised SLC could assist. | LT | 05.06.2024 |  |  | LT to provide contact details for PC to pursue 01.05.2024 The banner design has been drafted and will be submitted at the end of this week for printing. NE is liaising with SLC to have it printed with the expected turnaround time a few days, the intention is for this to be visible at the forthcomg P1 New Entrant session. 05.06.2024 PC banner recieved and stored in school, it was utlised during recent PC overview to new entrant P1 parents
PC07 | 06.03.2024 | End of Term Disco - PC confirmed this event for 12.06.2024 with a beach theme, children can come dressed in shorts and t-shirt. Photobooth and DJ to be booked. PF to provided disco flyer to share on school/PC social media and Parent Portal. Tuck shop and balloons to be ordered | PF/PJ/JH | 05.06.2024 |  |  | PJ to order Tuck shop/balloons for balloon arch and Photobooth. JH to book DJ 01.05.2024 DJ and Photobooth confirmed as booked. PJ will purchase Tuck Shop requirements with the inclusion of ice poles this time as the hall is usually very warm along with balloons for the balloon arch. PF to purchase some decorations and has provided disco flyer to HT which will be shared on Parent Portal and social media. 05.06.2024 Decorations and tuck purchased for forthcoming disco, social media updates also been shared, support required for disco set up/coverage and clear up. PF to comms the PC members and volunteers
PC08 | 06.03.2024 | School Sports Day (05.06.2024) - PC confirmed Cake sale (if the weather is warm ice lollies to be included) in the AM session with flyer to be provided to school for social media/Parent Portal with inclusion of request for parents/carers to hand in items for sale. If the weather is wet these can be sold within school. | PF | 05.06.2024 |  |  | PF to provided Bake Sale Flyer to LT to share on school social media/Parent Portal with the inclusion of the caveat around the weather 01.05.2024 Bake Sale poster was shared with HT. Discussion took place around procuring some cakes/biscuits from local shops (Morrisons) or organisations (Greggs/Tunnocks) LR and PF to make contact 05.06.2024 Greggs/Tunnocks contacted but unable to unfortunatley assist. Bake Sale postponed due weather forecast. Social media post shared to thank parents/carers for any donations recieved, these will be sold in school in the coming days
PC20 | 01.05.2024 | End of Term Raffle - discussion took place around LR proposal to facilitate an end of term raffle to help raise funds |  | 05.06.2024 |  |  | LR to contact Tunnocks / VC to contact Gladiators Basketball Team and NMcF to liaise with her workplace. A social media post is to be shared by the PC to enquire to seek raffle sponsors. 05.06.2024 Attempts were made to seek prizes/external support for a potential raffle but little response. Discussion took place around the timely approach to this to ensure we give ourselves the opportunity for maximum response, this to be factored into future event planning
PC03 | 06.03.2024 | PC Church Rep to be appointed | PF/LR | 04.09.2024 |  |  | PF/LR to speak with Fr Morton on 10.03 to understand requirements 01.05.2024 LR and PF spoke with Fr Morton who advised that the Rep is of his choosing and that he would advise in due course. PJ suggested an individual from the church community who may be interested, she will speak with them and as that they make contact with Fr Morton 05.06.2024 PF/LR have reminded Fr Morton of request and will continue to seek an appointment, LT will also discuss in order to progress 04.09.2024 Linda Duffy has been appointed as Church Rep and attended AGM
PC05 | 06.03.2024 | P1 New Entrant Session (21/29/05.2024) PC advised they would be present to share Parent Council information. PF can cover with PJ to confirm. PF to update PC Flyer for distribution. PC also suggested distribution to parents on first day of new term small welcome pack of tea/bag/biscuit and poem which was agreed | PF/PJ | 04.09.2024 |  |  | PF to update PC Flyer for New Entrant Session. PC to purchase parent welcome pack 01.05.2024 PF has updated Parent Council Flyer to share at the forthcoming P1 New Entrant session, this will distributed along with information on 'my name tags' initiative. PF asked LT if the PC Board could also be in view for the session. PF will purchase the welcome pack components for the start of the new term in due course 05.06.2024 PF attended new entrant P1 session, PC flyer confirmed as provided within parent pack. PC board notice board on view in school foyer and new PC banner was in background for PC overview to parents. PF to purchase on behalf of PC the welcome pack for new P1 parents in the summer break 04.09.2024 PF still has the welcome packs for P1 which will be handed out next year. 02.10.24 PF has created a new flyer to be given out at the start of the next year for the new intake as well as the welcome pack.
PC11 | 06.03.2024 | PC Board - PC welcomed the use of a school notice board to promote the PC and it's current committee members, there will also be an update to the Nursery noticeboard to support | LR/PF | 04.09.2024 |  |  | LR will work on designing this with the inclusion of PC committee members photographs and collect school board and update Nursery board 01.05.2024 LR completed a moveable notice board, PC requested this is visible in school at all times to promote the Parent Council and aid with faces to names of committee members. The Nursery notice board still requires a poster to be created - PF/LR to work on 05.06.2024 PC notice board in situ in school foyer. PF to provide HT with flyer for Nursery noticeboard which will complete action 04.09.2024 Flyer being shared with GT and is now visible in the Nursery foyer. A new poster will be made for the nursery. PF/LR will work on this. 02.10.24 It was discussed that all notice boards have been completed and that there is a flyer on the nursery notice board promoting the parent council. These will be updated as and when required.
PC17 | 06.03.2024 | P7 Leavers - Discussion took place around the following: - P7 Hoodies - P7 Leavers mass/show - P7 event - Piper for last day | All | 04.09.2024 |  |  | The PC will contribute to the P7 leavers hoodies/food as per usual arrangements, (this will total £300) they will also decorate the balloon arches which can also be used for Nursery leavers and provide helium balloons - this will be done at start of last week of term in the gym hall. P7 leavers event - HT to discuss with P7 however, any out of school event similar to that of last year would be for parents to organise. P7 leavers normally leave on last day to all school in attendance and arch by P6 with music playing in the background, if a Piper was a parental request it would require to be funded and organised by them 01.05.2024 PC to provide above funding to HT as agreed along wit provision of balloons. Leavers events planned through HT inconjunction with P7 pupils. VC advised of one of the P7 parents looking into the potential of a Piper and will revert back at next meeting with an update 05.06.2024 PF/LR to organise balloons for next weeks P7 Leavers show. Potential Piper was intimated to be available however PC suggested this was arranged with P7 parents and to take forward with HT
PC21 | 05.06.2024 | Parent event for new term - PC keen to host a Parent/Social evening in the new term | All/PF | 04.09.2024 |  |  | Discussion took place around a potential Parents event at the start of the new term, this would take the form of bingo/quiz night and BYOB. PF to confirm church hall availabilty/hire with Fr Morton. 04.09.2024 A social evening of potentially games/Bingo night has been booked in the church hall for 0911. Further discussion about organisation etc needed with an informal PC meeting to take place to plan these.'Save the dates' to be sent to HT for circulation and shared on PC social media. 02.10.2024 This has been postponed due to other events happening around the same time as also staffing/cover available fo the event.
PC22 | 05.06.2024 | First Sunday of the month family mass | All | 04.09.2024 |  |  | LT advised she intends to continue in the new term with extending an invitation to families to attend the first Sunday of every month to 10am mass. The PC to discuss church hall availabilty/hire with Fr Morton for tea/juice and biscuits after this mass for families to come together 04.09.2024 A Bake Sale is arranged following family mass on 06.10. Invitation is open to families and parishioners with details to be shared via the church bulletin/PC and school social media and Parent Portal. 02.10.2024 Bake sale has been advertised and is happening on Sunday.
PC23 | 05.06.2024 | PC Action and Decision log and socal media links addition to school website | LT | 04.09.2024 |  |  | PC requested that the Action and Decision Log is shared onto the School website following updates from each meeting along with links to the Parent Council social media 04.09.2024 - This tem now actioned and complete
PC24 | 04.09.2024 | Receipts for purchases - JH requested that all receipts for purchases were original paper copies provided to him/shared via email. | All | 04.09.2024 |  |  | JH to provide his email address to the group. 02.10.2024 JH provided his email to the group chat and has already been used for purchases.
PC25 | 04.09.2024 | School Cash Donation - LT requested £100 on behalf of Mrs McAlpine for Mini Vinnies | JH | 04.09.2024 |  | Decision | The PC agreed to support this, JH to progress. 02.10.2024 JH had gived Mrs Mc Alpine the donation and a thanks was given.
PC26 | 04.09.2024 | Children's Liturgy - Father Morton requested PC support in regards to the proposed re-introduction of the Children's Liturgy | PF/NE | 04.09.2024 |  |  | PF/NE will repost on social media to promote and support Fr Morton's request for leaders and helpers. 02.10.2024 Children Liturgy Volunteers has been reposted on both our social media platforms.
PC 27 | 04.09.2024 | PC Elections/Vacancies/departures - Two yearly tenure of current posts (Chair/Secretary and Treasurer) require to stand for re-election | All | 04.09.2024 |  |  | GMcA stood down as secretary and VC has now left the PC as her child is now in Secondery school. PF and NE thanked both for all their time and hard work they put into the PC. PF/NE and JH were voted to retain their current roles. PJ and LR have been elected as joint secretaries.
PC29 | 04.09.2024 | Meet the Teacher Event - Discussion took place about the the time of the meet the teacher and it was a possible disadvantage to many working parents | All | 04.09.2024 |  |  | LT advised that the turnout was 86, higher than previous years and teachers Working Time Agreement also had to taken into consideration.
PC30 | 04.09.2024 | Homework Policy - Discussion took place on the new homework policy | All | 04.09.2024 |  |  | Clarification was given by LT on the new homework framework and content. This may be revisited at next meeting. 02.10.2024 Was discussed again and agreed that we will closed this action point however if parents have got any concerns they can contact us or LT directly.
PC32 | 02.10.2024 | Christmas Gifts - PC have offered to contribute money to each class and nursery for Christmas Gifts. | JH | 06.11.2024 |  |  | It was discussed that in previous years we have provided the school and nursery money to buy gifts for each class for Christmas. PF suggested covering panto costs however, LT advised that this has been organised already to visit the school and costs have been covered It was agreed that JH will provide the school with £50 for each class as well as the nursery. 06.11.2024 JH has provided the school with £50 for each class to buy each class a gift for Christmas.
PC16 | 06.03.2024 | Future Fundraising - PC requested to work with LT for 2024/25 planning of events (and required Lets) which incorporate fundraising in order to space out the financial cost to Parents/Carers | PC/LT | 06.11.2024 |  |  | LT to extend invitation to PC in June to progress 01.05.2024 LT agreed to meet with PC in June to progress and will provide date for this shortly 05.06.2024 PF/NE to meet with LT next week to discuss lets and events for new term. An informal meeting of PC to take place before school ends for summer break to discuss/plan for September to December term - PF to circulate to PC members to confirm a date 04.09.2024 PC members met informally before summer break. PF/NE met with LT to discuss and agree lets along with fundraising events for the new school year. PC will meet again informally to plan the forthcoming Bake Sale and Parent/Carer soclal event. 04.09.2024 PC confirmed the addition of a Virgin Money digital grant which was awarded to the school and nursery for £2000 (for digital/STEM items) along with Tesco Burnside donation of £320 from the summer lending library that we participated in.PC to work with HT regarding the expenditure of these. 02.10.2024 We agreed to withdraw the social event this year due to clashes with other events in school and the church. The grant from Virgin Money still has to used. LT will have a further discussion with the staff but the ideas of digital printers, cameras, or art resources were discussed. LT will revert back to PC for purchases and the report to Virgin Money is due on January. NE has been in touch with Morrisons but she is waiting to hear back from them with dates available for a shake a bucket fundraiser. 06.11.2024 JH researched the criteria for the grant. We reported that it needs to ideally be spent before Christmas (due to holidays), we can use any shop, however it won't cover VAT. LT asked if we could get an external hard drive and a camera for every class including the nursery and also an extra 6 cameras for group of children to use if possible (part of the Technology plan). LR husband will research best cameras and hard drives and will report back to PC ASAP. 08.01.2025 19 cameras, and storage were purchased using the grant money. A special thank you to Mrs D for writing the report which is being submitted on the 09.01.2025.
PC34 | 02.10.2024 | School Football Team - someone has been in touch regarding starting a school football team if the school is interested. | PC | 06.11.204 |  |  | PF advised she had contact from a parent advising that her son is a qualified and trained SFA referee, she asked if the school would be interested in starting a football team that he can lead. LT welcomed this, she advised she would get in touch with Karina (Active Sports co-ordinator) for help and advice. lT advised that altough the gent holds a PVG, he would need another seperate PVG for working at the school. PF will forward the details on to LT. 06.11.2024 PF was still to forward the details to LT. 07.11.2024 PF has forwarded details, action complete. 08.01.2025 The coach has visited the school and is in process of completing all paperwork. Once completed he will be able to begin the sessions
PC 35 | 06.11.2024 | Virgin Bank Grant - LT has advise what the school would like the PC to purchase with the grant money | PC | ASAP |  |  | LT had a discussion with the staff and they agreed that they would like to purchase cameras for each class and and external memory drive to store the photographs and if possible an extra 6 cameras for the groups of children to use. LR and GR will do some research on the best available and will contact PC on findings as soon as possible. 08.01.2025 See PC 16 for outcome
PC 36 | 06.11.2024 | Mr Morecombe after school chess club | PC |  |  |  | PC would like to formally thank Mr Morecombe and share their appreciation to him using his own time to lead after school chess club .
PC 42 | 05.02.2025 | Formal thanks to departing Teachers | PC |  |  |  | The Parent Council wished to fomally thank both Miss McEnaney and Mrs Dickson for their time and support in school and particularly to Mrs Dickson for her IT support to the PC. We wish the both well in their new schools and roles
PC14 | 06.03.2024 | School Lottery Proposal - PC advised of School Lottery proposal that other local schools patriciate in. The information pack was shared with HT and PC will also share the details in their update in the a forthcoming HT newsletter with a doodle poll for feedback | PC/PF | Spring 2025 |  |  | PF to include in HT monthly newsletter and google poll to be set up 01.05.2024 It was agreed to progress this item in the next school term and to allow for PC social media to be set up in order to promote 05.06.2024 This item to be carried forward for progression in new term 04.09.2024 The PC will explore this in the coming months to begin as soon as possible. 02.10.2024 After discussion it has been agreed that we will leave revisit this in Spring, we are aware of the rising costs at this time of year. 08.01.2025 PF mentioned that she is aware of a new lottery from Parent Kind that is being launched soon. PF will receive more information on this and will discuss with NE. We are keen to engage parents more to ensure it would benefit all and lotter would provide this. 05.02.2025 This item to be further discussed within the PC at a forthcoming informal meeting. 05.03.2025 It was agreed at the informal meeting and confirmed at PC meeting that this item will be reconsidered at a later. We will create a google form for parents to vote and give their opinions on ways we can fundraise for the school through the parent council. This will be on a new action point. | https://mcusercontent.com/b9c117346e8204e58a48bb6f1/files/0c88861a-29c8-525c-b83c-2033ceaffaae/YSL_Leaflet_2021.pdf
PC18 | 06.03.2024 | PC advised it is keen to pursue financial support through Tesco tokens and also potentially look into registering as a charity | PC | 08.01.2025 |  |  | Parent Council to contact Tesco and obtain paperwork to complete for charity registration 01.05.2024 NE made contact with Tesco Burnside and Tesco Dalmarnock. Both have differing process however, a letter is requied to be submitted with a structured request of the requirement for financial support to which there are 3 tiers, if chosen all of the tiers would need to be suitable for the request to allow Tesco to promote this should the request be chosen. The token promotion if chosen means you are visible in up to 10 stores. PC to seek further clarity on the application process and report back at next meeting 05.06.2024 PF/NE contacted both Tesco Burnside and Dalmarnock. 3 options available with above tokens being the most challenging application to progress. HT issued letter verifying PF/NE positions which will be handed in with a request to be put forward for both bucket collecting and donation via book library loan. It was agreed in terms of bucket collecting this would be best for after the summer break if feasible. 04.09.2024 PF received cheque from Tesco for book lending library which was a total of £320. 'Shake a bucket' is scheduled for 07.09 at Tesco. LR/PF/NE/NMcF/BL/ML/JH will attend. Bucket collecting scheduled at Morrisons before christmas. PF/NE to complete form for charity registration. 02.10.2024 PF/NE still to complete charity registration. 06.11.2024 PF suggested contacting Morrisons for a bucket collection near Easter. Regarding Charity application, it was discussed we may need to move quicker for registration as some banks are starting to make charges to some accounts (but not charity) 08.01.2025 NF will contact Morrisons once again for a possible date close to Easter for a bucket collection. Once we have a date a schedule for cover will be arranged. The charity application has been postoned due to illness. We are still very keen on carrying this out and will hope to be completed very soon. 05.02.2025 NE advised Morrisons have confirmed the date of 29.03.2025. PF to update PC social accounts nearer the time
PC31 | 02.10.2024 | Mother's Day Breakfast concept - PC suggested the idea of a Mother's day breakfast after Family Mass on a Sunday. | JH | 05.03.2025 |  |  | PF reiterated an idea by JC - when the children used to serve breakfast to parents and parishioners. We all agreed this would be a good idea to try to tie into Mother's Day celebration after Sunday Family Mass. It was agreed we should pencil it in for 02.03.2025 as this was the mass closed to the day. 06.11.2024 We are very keen on carrying out this event,LD has said it was well attended previously. We will discuss furtherin the NY the options available regarding food etc. 08.01.2025 PC agreed that the Mothers Day breakfast will go ahead on 23.03.2025 after 10am mass. PF will contact Linda to arrange the hall let. PC will hold an impromtu meeting to finalise all the details. 05.02.2025 PF advised Linda returns from holiday at the end of this week and will be in contact regarding PC request for availability of church hall. The group agreed to progress this event and will discuss further at the forthcoming informal catch up 05.03.2025 After much discussion it has unfortunately been decided that we cannot proceed with this due to very few helpers availble. We may look again next year.
PC33 | 02.10.2024 | Corporate Card - suggestion of a corporate debit card beiing issued inconjuncton with the PC bank | JH | 05.03.2025 |  |  | JH reported that he has had some communication with the bank regarding a change over to Nationwide. He said it should be possible to recieve a debit card and he would look into it and revert back. 06.11.2024 JH has not had the opportunity to contact the bank regarding a card so this will be carried on to the next meeting. 08.01.2025 JH still has been unable to contact the bank during the christmas break but it was still agreed that it was worthwhile and a massive benefit to the PC. 05.02.2025 JH updated to the group to advise possible to obtain corporate debit card thorugh the PC bank account, the group agreed 1 max 2 would be required. JH will confirm no charges would arise from this and progress next steps 05.03.2025 As PJ purchases the largest amount for the PC events it has been decided that she will have a card in her name to pay for these purchases.
PC 38 | 08.01.2025 | Cameras for the nursery | PC | 05.03.2025 |  |  | The nursery have mentioned that they would like some more cameras to take photos for evidence. PC has asked LT if she could ask the nursery to complete a wishlist and return it to the PC for purchase. 05.02.2025 PF/NE and JH in posession of nursery request list and clarified the ask within the list. JH will progress with purchase. 05.03.2025 JH has purchased the camera and the nursery are currently using them. They are very thankful for the cameras.
PC 40 | 08.01.2025 | Sacramental Parties | PC | 05.03.2025 |  |  | It was discussed about providing the classes that are having the Sacraments with a party. It was agreed that we will provide the classes with cake and snacks for parties (13th March and 14th May). Sacrament party for the Primary 7 will start next year. 05.02.2025 Discussion took place around numbers for each group of children and best place to purchase, NMcF to check a local bakery and PF local supermarket, if not, COSCO will be the fallback with the first order to be placed ASAP 05.03.2025 NMcF advised cakes from a local bakery were going to cost too much therefore PJ has ordered a cake for the reconcillation party and will collect prior to party. She will then order one for the next party nearer the time.
PC 43 | 05.02.2025 | School uniform upcycling accessibility | ALL | 05.03.2025 |  |  | Discussion took place around the accessibility for parents/carers of uniform of uniform being handed into school. HT advised that she will have this available on Parent Reporting evenings and also as the weather improves could be placed on hanging rails at the end of the school day for people to access readily. Further to this was the suggestion of party clothes being handed in that could be offered and available to anyone should they need it.
PC 41 | 05.02.2025 | Asda Cashpot for Schools | PC |  |  |  | The Parent Council advised of the final figure for the recent Asda Cashpot for Schools initiative of £238.31 and wished to thank the school community most sincerely for this. They have received notification that the funds will be deposited by the end of March
PC44 | 05.03.2025 | Disco photo booths | ALL | 07.05.2025 | 07.05.2025 |  | There has been some feedback that they children would like a photobooth again at the disco. PC discussed about having one at the end of year disco. Our regular photobooth can be quite costly and does not make any money therefore PJ will look into other potential photobooths for the upcoming summer disco.
PC48 | 05.03.2025 | Primary 1 Entrants programme | PF |  | 07.05.2025 |  | PF will purchase the gifts required for the parent of the Primary 1 children on their first day. LT advised the settling in visits are on 21.05.2025 and 28.05.2025. PF will introduce the Parent Council on 28.05.2025 07.05.2025 PF has purchased and has made the gifts for the new P1 parents for their first day.
PC49 | 05.03.2025 | X (Twitter) update | ALL |  | 07.05.2025 |  | SLC no longer using X as a sharing platform (except for emergency posts) and are moving over to Blue Sky. There is no requirement yet for the school or PC to move to Blue Sky but LT will inform us when this is necessary. 07.05.2025 Link this action with PC13.
PC47 | 05.03.2025 | Primary 7 Leavers | JH | 07.05.2025 | 07.05.2025 |  | Discussion began on what the PC will donate to the Primary 7 school leavers. In the past PC contribute to pizza and balloons. JH will look into an increase into the donation amount. 07.05.2025 JH and PF discussed that we will donate £100 to the P7 leaver fund for Pizza etc. PF will also purchase balloons for the leaver shows.
PC50 | 07.05.2025 | Ice-Cream Van School treat | PC | 07.05.2025 | 7.05.2025 |  | NE has advised that the ice-cream van has been booked for 23rd June to for all school and nurseryl pupils and staff to receive an end of year treat.
PC19 | 01.05.2024 | Parent Pay - discussion took place around utilising Parent Pay to allow Parents to pay online for PC events | LR | 05.03.2025 | 03.09.2025 |  | "LT advised that Mrs McColgan is able to extract reports which would demostrate payment for events. PC to consider this option in the new school term 05.06.2024 Further discussion took place around the use of Parent Pay and it was agreed to trial this in a PC event in the new term 04.09.2024 PF advised there are other online payment options available which other school uses. It was agreed more information would be needed before a decision was made on how to progress. 02.10.2024 Discussion took place about the possible use of a card machine such as 'sumup' as a way for receiving payments from parents during fundraisers, this requires further discussion. 06.11.2024 Discussion took place about the pros and cons of having our own card reader. LR will research the various readers noting costs etc and relay this back to PC for a decision. 08.01.2025 LR discussed her findings on contactless payment machines. It was noted that they all had transaction charges of roughly 1.75% and PC agreed it would not be worth our while. PC will meet with Mrs McColgan to the possible use of Parent Pay, pros and cons. PF will contact Parent Kind if they have any information on contactless payments. 05.02.2025 PF had some discussion with Mrs McColgan regarding the parental/carer uptake on this and further to this the PC suggested trial usuage potentially in March for the school and thereafter the PC may utilise for the end of term disco. Further discussion to be had at the forthcoming informal meeting. 05.03.2025 PC discussed about the possilble confusion over online consent for disco and then cash for tickets. This has resulted in a trial of paying for tickets through parent pay. LR mentioned after looking into parent pay that schools have a charge per transaction for using this service however LT is not aware of any charges to them and believe if there is then it is the South Lanarkshire that would cover it. 07.05.2025 It has been been agreed to trial Parent Pay for Disco tickets after a discussion with Mrs McColgan. She will add a Disco payment nearer the time and has advised that we can still take money for tuck shop and also pay at the door is necessary. Information will be sent out to parents when permission slips are being sent out. 03.09.2025 The summer disco last term introduced parent pay as a method of payment for tickets. This was deemed to be a success and the PC will continue using ParentPay as a method of payment." | https://www.sumup.com/en-gb/payment-solutions-made-simple/?utm_source=google&utm_medium=cpc&utm_campaign=6476940146&utm_content=6476940146_98915341429_664841383354&utm_term=sum%20up%20card%20payment&gad_source=1&gclid=EAIaIQobChMI_JSPp9LwiAMVI5KDBx1j1hmaEAAYASAAEgIIB_D_BwE
PC28 | 04.09.2024 | School Uniform Suppliers - PC raised concerns of interactions with the current uniform supplier whilst purchasing items for return to school | PC | 07.05.2025 | 03.09.2025 |  | "LR queried change of school uniform supplier due to cost and late delivery. LT stated there would need to be a consultation with parents if any change was to be initiated. Discussion to take place at next meeting. 02.10.2024 This will remain open and discussed further in the new year. 08.01.2025 PC discussed that it before we have a parent consulation on Uniform we will hold a discussion with Peter from LogoXpress to air our concerns, which will be collated prior to meeting. 05.02.2025 PF to progress discussion with Peter from LogoXpress 05.03.2025 PJ has taken on the task of contacting Steven from LogoXpress and will update PC at next meeting. 07.05.2025 Contact has been made with LogoXpress. We have been advised that there has been a change to management and current manager Frances is out of office until Thursday when she will return our call. We have also been advised that they have already made changes due to problems with suppliers last year. They will be coming out on one of the P1 entrants programme but are unsure if it will be manned or not. 03.09.2025 PC discussed there has been an improvement with the school uniform supplier from the previous year and has not had any complaints from parents."
PC13 | 06.03.2024 | PC Social Media - the group updated LT on the new PC logo and advised they are in the process of setting up a new Instagram page, this along with X (Twitter) they hope to further share and promote to enable parent/carer news/updates. All paperwork will carry the logo along with the school/nursery logo | PF | 05.03.2025 | 01.10.2025 |  | PF to update and share in conjunction with IT support from Mrs Dickson 01.05.2024 PF met with Mrs Dickson who provided social media support, some password issues meant another meeting to take place to progress 05.06.2024 PF to meet with Mrs Dickson in new school term to progress. 02.10.2024 This has not progressed as PF has been unable to meet up with Mrs Dickson due to her class commitments. PF will try to look into linking the facebook and twitter with a PC instagram page. 06.11.2024 Due to other commiments from PF and Mrs Dickson they have been unable to arrange a time to meet. This will be difficult in the lead up to Christmas so will look at it again in the new year. 08.01.2.25 PF will speak to Mrs Dickson as soon as possible to try to solve the issue. 05.02.2025 Unfortunatley Mrs Dickson has now moved post out of school. PF to contact Miss Thompson to see if she can assist. 05.03.2025 PF has confirmed she will arrange a meeting with Miss Heather Thomson to discuss any support she can offer the PC regarding the Social Media updates. 07.05.2025 Miss Thompson has offered to help the PC with linking our social media accounts. As well as including our changeover to Blue Sky (PC49) 03.09.2025 PF is still continuing to try and link PC Facebook page with new Instagram page. PC move to Bluesky will happen at the same time as the school move. LT will discuss with Mrs Scott about when this will happen. 05.10.2025 PF has been unable to link Instagram with PC facebook page without having to start up a new facebook page. As a result of this we have agreed to do seperate postings on al social media pages including Facebook, Instagram, X(until disallowed) and Bluesky.
PC 37 | 06.11.2024 | Athletics and Netball Kits | PC | 05.03.2025 | 01.10.2025 |  | "It was brought to attention at a recent sporting event that the school may be short of some netball or athletic kits. LT will speak to the appropriate staff to see what is required and if the PC are able to help with this purchase. 08.01.2025 Mrs Thiems has not yet got back to the PC regarding what is required to be bought for each of the teams. Once this has been communicated we will look into supplying these teams with their kits. 05.02.2025 LT advised Mrs McColgan progressing with costings and related sizings, initial returns suggested differing sizes would need to be acquired to meet the needs of the school. 05.03.2025 LT updated parent council that the company they were looking at was charging £15 per t-shirt including printing and are going to look at alternate companies for quotes. LR knows someone who creates personalised clothing and will also contact them and will bring a sample to the school when she receives it. 07.05.2025 LR sourced the t-shirts and the school has now been in receipt of 50 athletic t-shirts and will look into the possiblity of waterproof jackets for the school also. 03.09.2025 LR has managed to price the sports jackets which are £16 each She will send this to LT along with the sizes . Once requests have been made this will be passed onto the PC for confirmation. 05.10.2025 LT has provided the sizes and amounts of jackets that they would like for the sports teams. The PC has approved and the order has been placed.
PC53 | 03.09.2025 | Masterclass & Mini Vinnies Donations | JH | 01.10.2025 | 01.10.2025 |  | LT has asked on behalf of Mrs McAlpine if PC could donate £100 for the Mini Vinnies. As well as £200 as a starter fun for the new term of Masterclasses following discussion the resources can be costly. JH will provide the school with these donations. 01.10.2025 JH provided the school with the required donations which they were very grateful for.
PC45 | 05.03.2025 | Plastic Water Bottles | PC | Ongoing | 13.11.2025 |  | NMcF made PC aware that there is a lot of waste from plastic water bottles at the disco as the children are just putting them into the bin. She asked if there was anything that the school or nursery could use them for. PJ mentioned that we previoulsy did the bottle collection option at Lidl. LT said she would speak to Mr Wood on how the school could use them and speak to the children to either use them for projects or to raise money for the school. 07.05.2025 LT has been unable to speak to Mr Wood due to other commitments. We discussed that we will keep any water bottles from the disco until we have an outcome 03.09.2025 After further discussion and the impact on the environment it may be a possibility to stop the bottle water and provide water in cups. 01.10.2025 Discussion too place of the practicality of using cups (the amount required, cleaning, misplaced etc) and it was decided that we would ask children to bring their own water bottle. We will inform parents through Parent Portal and Social Media. We will provide or refill or any child who doesn't have one or needs more water. 13.11.2025 Debrief took place on using own water bottles at the Autumn disco. We had positive feedback and an overall positive outcome for all. We will continue this for all future discos.
PC52 | 07.05.2025 | Parental Involvement | PC | Term 1 25/26 |  |  | PF and NE has began creating a Googleform for parents asking what they would like from the PC. They have asked if members of the PC have other ideas for questions to ask. 03.09.2025 CL has offered to help create the googleform and get it out to parents as soon as possible to ensure we can discuss the results as the next meeting. 01.10.2025 CL has created a googleform for the school parents. PC is very happy with the questions and this will be sent out to parents via Parent Portal. 13.11.2025 LT has offered the PC the use of some chromebooks and Ipads for the PC to set up the questionnaires during the family learning afternoon. After this event the PC will collate the results and discuss findings.
PC58 | 13.11.2025 | Christmas fundraising | PC | Term 2 |  |  | PF has a voucher for a Christmas Show and Santa Visit which the PC will raffle (possibly through Parent Pay - at the same time as disco tickets). Christmas Bonus Ball will also be running during both School Christmas Shows and the Nursery Nativity.
PC59 | 13.11.2025 | Confirmation Celebration | PC |  |  |  | Confirmation is on 25th November, and to celebrate, the Parent Council will be providing a cake for all P7 pupils on Thursday 27th.
PC61 | 13.11.2025 | Father Morton Farewell Plans | PC | 07.01.2026 |  |  | As a PC would would like to participate in the farewell plans for Father Morton in February. PC will contact LD with how we can help and support this event.
PC56 | 13.11.2025 | P7 Hoodies | JH | 04.02.2026 |  |  | PC will provide LT with the funds for the P7 hoodies. Costs will be discussed at next meeting. 08.01.2026 School has began purchasing the hoodies. JH will check that the funds have been transfered to the school. 04.02.2026 PC funds paid to school and hoodies ordered
PC54 | 03.09.2025 | P7 Leavers Social | PC | Ongoing |  |  | NE discussed a recent post on local page on social media regarding a P7 leavers event. As a PC we addressed this and concluded we cannot endorse this due to many factors such as cost of the school day and as a PC we already contribute to many P7 events and treats. School currently ask P7 what they want to do for their leavers week and this is actioned. We touched on the idea of the summer disco being extended for P7 only as a treat. This will be further discussed. 01.10.2025 Discussion took place on changing disco time for summer but we thought that bringing it forward by 45 mins may not suit lots of working parents. We agreed to think of other possible options. 13.11.2025 PC agreed we still have time to decide on any changes to the school disco for P7s etc. 04.02.2026 After discussion, this item will remain open in case any further revisit required
PC60 | 13.11.2025 | Disco DJ | PC/JH | Ongoing |  |  | PC has received numerous feedback from parent helpers and children about the current DJ which we use for the school disco, some being that there was too many games, very little dancing, song choice and not being able to hear her. LT will ask the pupils for their opinion on what they would like and we will take this feedback to her and ask for some changes to be made as deposit has already been paid. 08.01.2026 PC wil acknowledge and appreciate the input the children gave to the disco. 04.02.2026 PC acknowledged feedback recieved from pupils following recent Christmas disco and will explore for future discos. JH to book Summer disco DJ requesting same one as Christmas 04.03.2026 JH confirmed DJ is booked for the summer disco and currently it is hoped the same DJ from Christmas will be in attendance
PC61 | 13.11.2025 | Photo Booth (Disco) | PC/PJ | 07.01.2026 |  |  | After being unable to book a photo booth last summer disco due to supplier being fully booked we will begin the process of booking and contact previous company in the first instance for current costs. 04.02.2026 PC agreed to book Photobooth for Summer Discoas an annual occurence due cost. PJ to progress for the forthcoming June date 04.03.2026 PJ confirmed the Photobooth is booked for the summer disco
PC66 | 04.02.2026 | Easter Raffle Contribution | PC/JH | 04.03.2026 |  |  | PC to make a £100 contribution to the forthcoming Easter raffle, JH to transfer funds. 04.03.2026 JH confirmed he has transferred the funds as requested
PC71 | 04.02.2026 | Eco-Uniform Station | ALL | Ongoing |  |  | PC discussed the option to make uniform items readily available to parents/carers to help themselves to. All items are in very good used condition and freshly laundered. HT agreed to ensure visiible on School Reporting evenings/New Intake days and weather permitting placed outside the main school office entrance
PC74 | 04.03.2026 | Non-Uniform Days | PC | 04.03.2026 |  |  | PC stated there had been several non-uniform days in December and now over each Friday in Lent. Whilst the PC recognises Christmas jumpers/party days in December and fun Friday's in Lent, this could be seen as a cost to the school day for parents/carers. HT responded these days are optional to children and that of monetory contributions. The fun Friday days were decided upon by the varying committees the children sit on.
PC46 | 05.03.2025 | PVG Requirements | ALL | Ongoing |  |  | PF made PC aware that there has been a change to PVG rules which would include PC members requiring to have a PVG. LT has contacted SLC for more infomation. 07.05.2025 Information has been handed out to PC from SLC however it was not very clear. After HMIE inspection we will try and acquire more information. 03.09.2025 The majority of PC members have now got a PVG in place. The PC will need to ensure all current members and new members have completed the form. 01.10.2025 2 new PC members have been advised that they should have received an email to complete their PVG. If not NE will look into this and get it resent out. There is one outstanding current PC member still need to provide details for PVG. 13.11.2025 All PC members have either received their PVG registration or has already began the process. PC has also began registering some of the volunteer helpers. NE will need to reapply as her registration has gone missing and the link is no longer active. 08.01.2026 It has been discussed that adhoc volunteers who help out the PC at events will also need to be a PVG this will begin in due course. 04.02.2026 NE to progress x 2 applications 04.03.2026 NE resubmitted x 2 applications and awaiting outcome. 06.05.2026 NE has received all current PC members and volunteer PVG
PC62 | 04.02.2026 | Sacramental In-school Parties | PC | 02.05.2026 |  |  | PC agreed to purchase a cake for both the Reconcilliation and Holy Communion parties in school following the forthcoming Sacraments for P3 and P4. 06.05.2026 PC provided the cake for the Reconcilliation cake and has already been ordered and will be delivered to the school on day of party on 13.05.2026.
PC64 | 04.02.2026 | PC Google Form Feedback | PC/CL | Ongoing |  |  | PC in the process of analysing the feedback within the recently shared Google Form and will communicate this shortly 04.03.2026 CL still in the process of collating the information received, PC will respond at the earliest opportunity 06.05.2026 This item still needs to be discussed with all PC members.
PC73 | 04.02.2026 | Stationery | PC/PF | 04.03.2026 |  |  | PC recalled previous term where school budget was stretched to allow for purchase of school stationery: paper/marker and board pens/pencils etc. PC stated they were happy to make a contribution to a recent order that had been placed. PF to speak to office staff to progress 04.03.2026 PF discussed with school office stationery requirements and PC will progress to purchase requested items 06.05.2026 JH confirmed that stationery was delivered to the school and HT advised it was divided equally between the classes.

## Attendees
ROLLING Closed LOG: St Bride's School & Nursery Parent Council
Name | Position | Meeting Date
|  | 06.03.2024 | 01.05.2024 | 05.06.2024 | 04.09.2024 AGM | 02.10.24 | 05.11.2024 | 08.01.2025 | 04.02.2025 | 05.03.2025 | 07.05.2025 | 03.09.2025 AGM | 01.10.2025 | 13.11.2025 | 04.02.2026 | 08.04.2026 | 06.05.2026 | 03.06.2026
Louise Torrance (LT) | Head Teacher | [14 empty] | online | online
Nicola Ewing (NE) | Parent Council Chair |  |  | Apologies |  |  |  | online | [7 empty] | online | online
Paula Frederick (PF) | Parent Council Chair | [10 empty] | Apologies |  | Apologies |  | online | Apologies
John Hylands (JH) | Parent Council Treasurer | [14 empty] | online | online
Paula Jackson (PJ) | Parent Council Secretary |  |  | online |  | Apologies | Apologies | Apologies | Apologies |  | Apologies | Apologies |  | Apologies | Apologies | Apologies | Apologies | Apologies
Laura Robertson (LR) | Parent Council Secretary | [7 empty] | Apologies | [5 empty] | Apologies | online | online
Geraldine McAdam (GMcA) | Parent Council | Apologies | Apologies |  |  | Apologies |  | Apologies | Apologies | Apologies | Apologies
Bryan Lynch (BL) | Parent Council | Apologies | Apologies |  | Apologies | Apologies |  | online | online | online | online | online | Apologies | online |  | online | Apologies | Apologies
Michelle Lynch (ML) | Parent Council | Apologies | Apologies |  | Apologies | Apologies |  | online | online | online | Apologies | Apologies | online | online |  | online | Apologies | Apologies
Vikki Campbell (VC) | Parent Council | Apologies
Claire Muldoon (CM) | Parent Council | [5 empty] | Apologies | online | online | online | online | online | online | online |  | online | online | online
Joanna Clark (JC) | Parent Council |  |  |  |  | Apologies |  | Apologies | Apologies | online | Apologies | online | Apologies | online |  | online | online | Apologies
Nicola McFadden (NMcF) | Parent Council | [6 empty] | Apologies | online | online | online |  | Apologies | online |  | online | online | online
Ciaran Lang | Parent Council | [6 empty] | Apologies | online |  |  |  |  | online |  | online | Apologies
Christopher Brown | Parent Council | [14 empty] | online | online
Sean McGinty | Parent Council | [14 empty] | online | Apologies | online
Linda Duffy | Church Rep |  |  |  |  | Apologies | Apologies | Apologies | Apologies | Apologies | Apologies | Apologies | Apologies | Apologies | Apologies | online | Apologies | Apologies
Attended meeting
Attended online
Apologies